## Sheet1
Construction works (Tenders)
Sl No. | FY | TENDER NO. | Name of the work | Estimated Cost (in Rs.) | Awarded Value of the work (in Rs) | Awardee (Party) | WO/Agreement No. & Date | Date of Commencement | Schedule Date of Completion | Actual date of completion | Value of Completion | Expenditure Booked as on 31.03.19 | Reamrks
1 | 2017-18 | IIITG/WORKS/22/2017/3350 DTD.30.05.2017 | Tree Plantation work at IIITG permanent campus for the season 2017 thru P. K. Enterprise | 1,84,000.00 |  | PK ENTERPRISE | IIITG/Works/22/2017/3350 dated 30-05-2017 | 2017-05-30 | 2017-06-15 | 2018-11-14 | 184000 | 184000
2
3
4 | 2018-19 |  | Construction of 400 Seater Boys Hostel at IIIT Guwahati permanent Campus thru Hindustan Prefab Ltd. | 3350.95 Lakh |  | Arunoday Constructions (P) Ltd.) | HPL/RC/IIITG/2015-16/12 dated 29-09-2015 | 2015-10-07 | 2017-04-06 | 2018-05-31 | 3300.14 Lakh
5 | 2018-19 |  | Construction of Girl's Hostel at IIIT Guwahati permanent Campus near Mirza thru Hindustan Prefab Ltd. | 1277.02 Lakh |  | Shree Gautam Construction Co. Ltd.) | HPL/DGM ( C)/IIITG/2015-16/221 dated 19.11.2015 | 2015-11-28 | 2017-05-27 | 2018-05-31 | 1259.74 Lakh
6 | 2018-19 |  | Construction of Faculty Residence (2 nos Block) at IIIT Guwahati permanent Campus thru Hindustan Prefab Ltd. | 2305.86 Lakh |  | Tribeni Constructions Ltd.) | HPL/DGM (C)/IIITG/2015-16/222 dated 19.11.2015 | 2015-11-28 | 2017-05-27 | 2018-06-30 | 2212.86 Lakh
7 | 2018-19 |  | Construction of Academic cum Administrative Building at IIIT Guwahati permanent campus thru Hindustan Prefab Ltd. (M/S M.P. Khaitan) | 4205.61 Lakh |  | Shambhala Traders) | HPL/GM/TC/IIITG ACDA cum ADMN/2015-16/125 dated 23.12.2015 | 2016-01-02 | 2017-07-01 | 2018-07-31 | 3972.35 Lakh
8 | 2018-19 |  | Construction of Sub-Station building, Water Supply & Sewerage Work, Water Treatment Plant, Sewerage Treatment Plant & Fire Fighting at IIITG Permanent Campus thru Hindustan Prefab Ltd. | 476.96 Lakh |  |  | HPL/GM (Engg.)/Award/2016-17/56 dated 17/02/2017 | 2017-02-26 | 2017-08-25 | 2018-06-30 | 511.22 Lakh
9 | 2018-19 |  | Substation and External Electrification works (Phase - I) at IIIT Guwahati permanent campus near Mirza, under Kamrup (R) District, Guwahati thru Hindustan Prefab Ltd. x | 324.47 Lakh |  | Shambhala Traders) | HPL/DGM (C)/TC/Award/2017-18/33 dated 28.11.2017 | 2017-12-07 | 2018-05-06 | 2018-07-02 | 339.24 Lakh
10 | 2018-19 |  | Construction of Boundary Wall at IIIT Guwahati permanent campus near Mirza, under Kamrup (R) District , Guwahati thru Hindustan Prefab Ltd. (M/s Nareswar Choudhury) | 253 Lakh |  |  | HPL/DGM (C)/TC/Award/2017-18/43 dt. 22/12/2017 | 2017-12-31 | 2018-04-30 | 2019-02-15 | 206.28 Lakh
11 | 2018-19 |  | Construction and Development of internal road of IIITG Campus with WBM work and surface dressing, Mirza (Part-I) thru | 14,75,669.00 Group-A |  | PWD(Rd.), Assam (M/s Trishul Enterprise) group –A , thru PWD(Rd.), Assam (Bikash Thakuria) | W.O. no. CS/GRC/IIITG (DW)/2016-17/118/1824 dated 31-03-2017 | 31.03.2017 | 30.06.2017 | 2018-08-10 | 1475563 | 1475563
12 | 2018-19 |  |  | 15,09,503.00 Group-B |  |  | W/O No. CS/GRC/GDM/IIITG(DW)/2016-17/119/826 dated 31/03/2017 | 31.03.2017 | 30.06.2017 | 2018-07-06 | 1508596 | 1508596
13 | 2018-19 |  | Earth work in filling towards the left side of Academic-cum-Admin Building to accommodate car parking thru PWD(Rd.), Assam (Sri Bikash Thakuria) | 10,89,354.00 |  |  | W.O.no. CS/GRC/GDM/IIITG(DW)/2017-18/137/683 dated 28/02/2018 | 28.02.2018 | 27.05.2018 | 2019-03-08 | 1088831 | 1088831
14 | 2018-19 |  | Earth work in filling developing the Academic building front area for holding convocation/future function activities. thru PWD(Rd.), Assam (M/s Sarojini Real Construction Pvt. Ltd.) | 11,71,812.00 |  |  | W.O.no. CS/GRC/GDM/IIITG(DW)/2017-18/137/684 dated 28/02/2018 | 28.02.2018 | 27.05.2018 | 2018-08-30 | 1171729 | 1171729
15 | 2018-19 |  | Earth Work in filling in extension area of Girls hostel thru PWD(Rd.), Assam (M/s M&N Enterprise) | 5,92,129.00 |  |  | W.O.no. CS/GRC/GDM/IIITG(DW)/2017-18/137/682 dated 28/02/2018 | 28.02.2018 | 27.05.2018 | 2018-04-06 | 581820 | 581820
16 | 2018-19 |  | Earth work in filling in peripheral area of Faculty building thru PWD(Rd.), Assam (Sri Bikash Thakuria) | 4,36,000.00 |  |  | W.O.no. CS/GR/IIITG/4/17-18/417 dated 13/04/2018 | 13.04.2018 | 12.06.2018 | 2018-05-11 | 434154 | 434154
17 | 2018-19 |  | Earth work in filling in peripheral area of Girls Hostel building thru PWD(Rd.), Assam (Sri Bikash Thakuria) | 3,45,000.00 |  |  | W.O.no. CS/GR/IIITG/4/17-18/416 dated 13/04/2018 | 13.04.2018 | 12.06.2018 | 2018-05-14 | 344478 | 344478
18 | 2018-19 |  | Strengthening of the main Internal Road of the campus with one coat of WBM and carpeting over the same (Lane-III) thru PWD(Rd.), Assam (Borluit Construction & Co.) | 10,88,077.00 |  |  | W.O.no. CS/GR/IIITG/3/18-19/1875 dated 24.05.2018 | 24.05.2018 | 23.07.2018 | 05.12.2018 | 1088067 | 1088067
19 | 2018-19 |  | Strengthening of the main Internal Road of the campus with one coat of WBM and carpeting over the same (Lane-I) thru PWD(Rd.), Assam (Sri Bikash Thakuria) | 9,87,347.00 |  |  | W.O.no. CS/GR/IIITG/1/18-19/1987 dated 28.05.2018 | 28.05.2018 | 27.07.2018 | 20.10.2018 | 987247 | 987247
20 | 2018-19 |  | Strengthening of the main Internal Road of the campus with one coat of WBM and carpeting over the same (Lane-II) thru PWD(Rd.), Assam (Safikur Rahman) | 12,09,170.00 |  |  | W.O.no. CS/GR/IIITG/2/18-19/1874 dated 24.05.2018 | 24.05.2018 | 23.07.2018 | 20.10.2018 | 1209982 | 1209982
21 | 2018-19 |  | Laying of RCC Pipe of different sizes for cross Drainage and service Utilities at IIITG at Mirza for the year 2018-19 thru PWD(Rd.), Assam (Sri Pranab Thakuria) | 4,51,645.00 |  |  | W.O.no. CS/GR/IIITG/4/18-19/3978 dated 17.07.2018 | 17.07.2018 | 16.08.2018 | 25.07.2018 | 451645 | 451645
22 | 2018-19 |  | Construction & development by raising the low site in front of the Girls Hostel and the East side of Faculty Building by earth filling including providing Katcha drain thru PWD(Rd.), Assam (Sri Pranab Thakuria) | 4,82,000.00 |  |  | W.O.no. CS/GR/IIITG/8/18-19/7175 dated 28.09.2018 | 28.09.2018 | 27.10.2018 | 20.11.2018 | 475509 | 475509
23 | 2018-19 |  | Construction & Strengthening of approach road to Academic Building by the side of Cotton University approach road thru PWD(Rd.), Assam (Safikur Rahman) | 6,32,720.00 |  |  | W.O.no. CS/GR/IIITG/7/18-19/7176 dated 28.09.2018 | 28.09.2018 | 27.10.2018 | 09.01.2019 | 632684 | 632684
24 | 2018-19 |  | Development by raising low site of backside of Boys’ Hostel and Play field at IIITG for the year 2018-19 thru PWD(Rd.), Assam (Sri Pranab Thakuria) | 7,06,156.00 |  |  | W.O.no. CS/GR/IIITG/ 56/18-19/7064 dated 26.09.2018 | 26.09.2018 | 25.10.2018 | 20.10.2018 | 705890 | 705890
25 | 2018-19 |  | Strengthening of Approach road to faculty building thru PWD(Rd.), Assam (Sri Pranab Thakuria) | 6,22,063.00 |  |  | W.O.no. CS/GR/IIITG/ 5/18-19/7063 dated 26.09.2018 | 26.09.2018 | 25.10.2018 | 30.10.2018 | 621999 | 621999
26 | 2018-19 |  | Earth filling of Low Area for extension of playground at IIITG campus (90mX50m) for the year 2018-19 thru PWD(Rd.), Assam (Sri Pranab Thakuria) | 27,92,245.00 |  |  | W.O.no. CS/GR/IIITG/ 12/2018-19/11427 dated 24.01.2019 | 24.01.2019 | 23.04.2019 | 19.02.2019 | 2791692 | 2791692
27 | 2018-19 |  | Earth filling in the North Western Periphery of ESS Building at IIITG for the year 2018-19 thru PWD(Rd.), Assam (Star Motor & Transport) | 1,47,825.00 |  |  | W.O.no. CS/GR/IIITG/9/2018-19/ 11431 dated 24.01.2019 | 24.01.2019 | 23.03.2019 | 08.02.2019 | 147459 | 147459
28 | 2018-19 |  | Earth Filling of Low Area of Eastern periphery of Faculty Block-1 at IIITG for the year 2018-19 thru PWD(Rd.), Assam (Star Motor & Transport) | 1,18,312.00 |  |  | W.O.no. CS/GR/IIITG/10/2018-19/ 11149 dated 17.01.2019 | 24.01.2019 | 23.03.2019 | 06.02.2019 | 117888 | 117888
29 | 2018-19 |  | Development by raising low site of West Side of Boys' Hostel Building at IIITG for the year 2018-19 thru PWD(Rd.), Assam (Star Motor & Transport) | 1,75,646.00 |  |  | W.O.no. CS/GR/IIITG/8/2018-19/ 11430 dated 24.01.2019 | 24.01.2019 | 23.03.2019 | 19.02.2019 | 175604 | 175604
30 | 2018-19 |  | Earth filling of Low Area for Extension of Playgrounds at IIITG Campus (57.00m X 50.00m) for the year 2018-19 Phase-II thru PWD(Rd.), Assam (Sri Pranab Thakuria) | 15,47,682.00 |  |  | W.O.no. CS/GRD/13/IIITG/2018-19/ 13077 dated 27.02.2019 | 27.02.2019 | 26.04.2019 | 26.03.2019 | 1547429 | 1547429
31 | 2018-19 |  | Earth filling of Low Area in front of faculty residence for kid's playground for the year 2018-19 thru PWD(Rd.), Assam (Star Motor & Transport) | 2,48,416.00 |  |  | W.O.no. CS/GRD/14/IIITG/18-19/ 13078 dated 27.02.2019 | 27.02.2019 | 26.03.2019 | 15.03.2019 | 247822 | 247822
32 | 2018-19 |  | Internal Electrical works for laboratories of ECE & CSE Department | 3,54,969.00 |  |  | IIITG/Works/02/2018/4976 dated 30-10-2018 | 30.10.2018 | 2018-11-13 | 05.12.2018 | 354969 | 354969
33 | 2019-20 |  | 33 KV Permanent power supply line to the Campus ESS thru APDCL | Rs.330 Lakh |  |  | Deposit Work to APDCL (GoA)-IIITG/Works/APDCL/16/2016/3550 dated 07-07-2017 | 07-07-2017(Contract awarded from APDCL in Dec-2017) | 31-12-2017(Schedule Contract Completion of APDCL March-2018)
34 | 2019-20 |  | Earth filling in the area back of faculty residence to accommodate parking facilities | Rs11,34,202.00 |  |  | W.O.no. CS/GRC/GDM/IIITG(DW)/2017-18/134/685 dated 28-02-2018(PWD(Rd.), Assam (M/s M&N Enterprise) | 2018-02-28 | 2018-05-27 |  | 894213 |  | Contractor of PWD did not turn up for the balance work
35 | 2019-20 |  | Strengthening and Blacktopping of Approach Road to Boys' Hostel from Playfield road corner at IIITG campus, Mirza for the year 2018-19 | Rs12,33,065.00 |  |  | W.O.no. CS/GR/IIITG/ 11/2018-19/11428 dated 24.01.2019- PWD(Rd.), Assam (Sri Pranab Thakuria) | 24.01.2019 | 23.03.2019 |  | 1232931
36 | 2019-20 |  | Earth filling of Low Area for Extension of Playgrounds at IIITG Campus near Security camp for the year 2018-19 | Rs6,32,215.00 |  |  | W.O.no. CS/GRD/15/IIITG/18-19/ 13079 dated 27.02.2019- PWD(Rd.), Assam (Star Motor & Transport) | 27.02.2019 | 26.03.2019 |  | 6,31,576
37 | 2019-20 |  | Order for supply and installation of stand fan and ceiling fan | 607200 |  |  | IIITG/WORKS/6.2/2019/322 dated 11.07.2019, Supplied by Indigo Flame, Bamunimaidan, Guwahati | 12.07.2019 | 1 week |  | 607200
38 | 2019-20 |  | Installation of Campus Foundation Stone | 49281 |  |  | IIITG/WORKS/1.1/2019/1568 dated 29.07.2019, by Work done by Anil Thakuria | 29.07.2019 | 3weeks |  | 49281
39 | 2019-20 | NIT/IIITG/WORKS/MISC/2019/01 DTD.20.03.2019 | Construction of Embankment for pathway/cycle track to Boys Hostel from the rear side of Academic Building | 128270 |  | PRANAB THAKURIA | IIITG/WORKS/MISC/2018-19/031 dated 09.04.2019, by Sri Pranab Thakuria | 10.04.2019 | 25.04.2019 | 22.04.2019 | 115433
40 | 2019-20 |  | Construction of Bamboo Matted foot bridge | 40067 |  | SHREE GANESH ENTERPRISE | IIITG/WORKS/MISC/2019/454 dated 30.08.2019, Work done by Shree ganesh Enterprise | 30.08.2019 | 1 week | 07.09.2019 | 40067
41 | 2019-20 |  | Refurbishing works in Boys Hostel Kitchen Area | 33757 |  |  | IIITG/WORKS/6.3/2019/1568 dated 11.09.2019, Work done by Anil Thakuria | 12.09.2019 | 26.09.2019 |  | 33757
42 | 2019-20 |  | Earth Filling works in Sports Ground and Horticulture work in fornt of Admin Building | 12600 |  |  | IIITG/WORKS/MISC/2019/1611 dated 14.10.2019, Done by Shree ganesh Enterprise | 15.10.2019 | 22.10.2019 |  | 12600
43 | 2019-20 |  | Internal Electrical Works for laboratories of ECE & CSE Department | 360009 |  |  | IIITG/WORKS/02/2018/5035 DATED 20.11.2019 AND AMENDED DTD.18.12.2019, work done by M/s Brahmaputra Electricals | 20.11.2019 |  | 24.01.2019 | 354969
44 | 2019-20 |  | Enclosure for garbage storage area in Girls Hostel and faculty Residence area | 99929 |  |  | IIITG/WORKS/26/2019/1803 DATED 27.12.2019 | 30.12.2019 | 15.01.2020 | 15.1.2020 | 99929
45 | 2019-20 |  | Jail Fixing in Bys' Hostel Kitchen Verandah | 44850 |  |  | IIITG/WORKS/26/2020/01 DATED 01.01.2020 | 01.01.2020 | 15.01.2020 | 15.1.2020 | 44850
46 | 2019-20 | NIT/IIITG/WORKS/27/2020/01 DTD.13.02.2020 | Construction of a room for ATM at the entry gate, IIITG
47 | 2020-21 | NIT/IIITG/WORKS/26.2/2020/01 DTD.19.01.2021 | Erecting Chain Link Fencing at specified locations of the IIIITG campus to protect the sports field from stray cattle |  |  | Anushree Constructions | IIITG/WORKS/26.2/2021/24 DTD.01.02.2021 | 01.02.2021 |  | 30.06.2021
48 | 2020-21 |  | Dressing, filling, rolling and construction of RCC cricket pitch at West side of playground at IIITG for year 2018-19 Thru PWD (Rd.) | 1,14,140 |  |  | W.O. No. CS/GRD/IIITG/04/19-20/7407 dated 14/10/19---by Pranab Thakuria | 2019-10-14 |  |  | 1,13,602
49 | 2020-21 |  | Filling, Dressing, rolling of volley ball and basket ball court at east side of playground at IIITG for year 2018-19 Thru PWD (Rd.) | 1,05,534 |  |  | W.O. No. CS/GRD/IIITG/04/19-20/7408 dated 14/10/19----by Pranab Thakuria | 2019-10-14 |  |  | 1,05,534
50 | 2020-21 |  | Campus earth filling and road works in IIITG Permanent campus (sports ground top layer filling /development) thru PWD(Rd)- | 9,41,845 |  | Pranab Thakuria | W.O. No. CS/SKT/IIITG/50/2019-20/13340 dated 21-03-2020--- | 2020-03-21 |  |  | 9,41,302
65 | 2021-22 | IIITG/Works/31A/01 Date: 12-01-2022 | Construction of a 96 Seater Boys Hostel and Extension of the Girls Hostel at IIIT Guwahati permanent campus | 61000000 | 62525481 | Bikash Enterprises | Agreement dated 8th Mar-2022 | 03.03.2022 | 2023-12-02 | work under progress | work under progress
66 |  | IIITG/WORKS/20/2022 dt 10.05.2022 | Drilling of 400mm dia Bore well including installation of 12.5HP submersible Pump over Bore well at IIIT Guwahati campus | 700000 | 680100 | Sarmah Electricals |  | 2022-05-13 | 2022-06-10 | 2022-06-10 | 5,71,724
67 | 2022-23 | IIITG/Works/26.2/01 Date:26.05.2022 | Dining Hall shed near Boys' Hostel at IIIITG | 1346191 | 1174965 | AKD Construction |  | 2022-06-21 | 2022-08-05 | 2022-08-02 | 11,74,176
68 | 2022-23 | IIITG/Works/34_1/2022_23/03 Date:25.08.2022 | Construction of a Town Hall at IIIT Guwahati permanent campus Bongora, under Kamrup(R) District, Guwahati. | 7500000 | 7122583 | ABDUL QUDDUS | Agreement dated 27th Oct-2022 | 2022-10-05 | 2023-04-05 | 2023-06-15 | Bill under process
69 | 2022-23 | IIITG/Works/33.1/2022_23/02 Date:17.08.2022 | Construction of a Student’s Activity Centre at IIIT Guwahati permanent campus Bongora, under Kamrup (R) District, Guwahati. | 45500000 | 42961063 | ABDUL QUDDUS | Agreement dated 27th Oct-2022 | 2022-10-07 | 2023-07-03 | Work under Progress | Work under Progress
70 | 2022-23 | IIITG/WORKS/36.1/2022/105 dt 08.12.2022 | “Construction of Sports ground & courts at IIIT Guwahati permanent campus Bongora, Guwahati, under Kamrup (R) District. |  | 10376187 | Girdharilal & Sons Sports Pvt. Ltd | Agreement dated 29th Dec-2022 | 2022-12-27 | 2023-06-13 | Work under Progress | Work under Progress
71 | 2022-23 | IIITG/WORKS/17/2023/110 dt 18.01.2023 | Construction of a Canteen for Academic & Administrative Building, IIIT Guwahati | 1788025 | 1454228 | NICE TRADERS, Khikuchi Bazar, Azara, Kamrup, Assam-781017 | Agreement dated 21st Feb-2023 | 2023-01-25 | (Original works 25-04-2023) 15-07-2023 Extd. completion | (25-04-2023) | Bill under process
72 | 2023-24 | IIITG/Estab/55/2023/82 | Providing manpower for Operation and Maintanance of Electrical Substation and DG set, internal and external electrical installatios, water treatment plant and sewage treatment plant at IIITG |  | Service charge: ₹11200.00 Cost of Hypochlorite: ₹100 Micro Organism Mother culture for STP: ₹95 Micronutrient for STP: ₹55 | Brahmaputra Electricals | IIITG/Estab/55/2023/90 | 01.10.2023
73 | 2023-24 | IIITG/Works/37.1/145 | Construction of vertical expansion of classrooms at Academic cum Admin building of IIITG |  | 9497508 | Sri Narayan Deka | IIITG/Works/37.1/2023/159 | 19.12.2023
74 | 2023-24 | IIITG/Estab/54/2023/89 | Providing manpower, cleaning, sanitation and disposal of waste at IIITG |  | Service charge: ₹27500 Cost of waste disposal ₹19500 | Add Construction | IIITG/Estab/54/2023/89 | 01.10.2023
75 | 2023-24 | IIITG/Works/44/156 | Developing a lawn in front of Academic cum admin building |  | 2201000 | Daffodil Nursery Old | IIITG/Works/44/2024/178 | 20.02.2024
76 | 2024-25 | IIITG/Works/45/2024/179 | Architectural Consultancy for Phase 2 works of IIITG |  | 0.54% on executed work value. | CP & DS Associates | IIITG/Works/45/2024/197 | 06.05.2024
77 | 2024-25 | IIITG/Estab/3.3/2024/103 | Providing Office canteen service |  |  | Shree Ganesh Enterprise | IIITG/Estab/3.3/2024/108 | 28.03.2024
78 | 2024-25 | IIITG/Estab/58/2024/109 | Providing potable packaged drinking water at IIITG | ₹60 per 20 liter bottle | ₹36.00 per 20 liter bottle. | Shree Ganesh Enterprise | IIITG/Estab/58/2024/121 | 22.08.2024
79 | 2024-25 | IIITG/Works/Misc/26.2/2024/245 | Construction of fencing in front of faculty tower and around girls hostel |  | 832715 | Sri Anil Thakuria | IIITG/Works/Misc/26.2/2024/256 | 04.02.2025
80 | 2024-25 | IIITG/Works/43/152 | Providing and laying aditional water supply pipe line to the boys hostel from WTP |  | 590725 | Md. Mofijul Hoque | IIITG/Works/43/2023/173 | 30.01.2024
81 | 2024-25 | IIITG/Works/47/2024/206 | Partition of wall for modification work of girls hostel and Boys hostel |  | 441414.85 | Md. Mofijul Hoque | IIITG/Works/47/2024/215 | 05.07.2024
82 | 2024-25 | IIITG/Works/36.1/2024/239 | Remaining works of sports ground and courts at IIITG |  | 9248121 | Abdul Quddus | IIITG/Works/47/2024/261 | 11.03.2025
83 | 2024-25 | IIITG/Works/46/2024/196 | Repairing of internal roads of the campus |  | 1052225 | Pranab Thakuria | IIITG/Works/46/2024/214 | 05.07.2024