## 2025-2026
Sl No. | FY | TENDER NO. | Name of the work | Estimated Cost (in Rs.) | Awarded Value of the work (in Rs) | Awardee (Party) | WO/Agreement No. & Date | Date of Commencement | Schedule Date of Completion | Actual date of completion | Value of Completion
1 | 2025-26 | IIITG/Works/45/2024/179 | Making of ramp in front of Girls hostel, approach to the mess, penel, neat cement polishing in utensil clean area floor and painting of mess staff/store room at IIIT Guwahati | 1,68,372 | 1,20,606.00 | Deepak Das | IIITG/Works/45/2024-25/277 | 01.07.2025 | 26.07.2025 | 25.07.2025 | 1,30,392
| 2025-26 |  | Painting of rooms and toilets old boys and girls hostel at IIIT Guwahati Campus |  | 1,63,792.00 | Sri Anil Thakuria | IIITG/Works/2024-25/283 dated 11.07.2025 |  | 30.07.2025
| 2025-26 | IIITG/Works/2023-24/268 | Making of plinth protection for Faculty Tower I & II at IIIT Guwahati campus. | 2,89,980.00 | 1,94,661 | Deepak Das | IIITG/Works/45/2024-25/268/270 | 27.05.2025 | 27.06.2025 | 26.06.2025 | 1,94,445
| 2025-26 |  | Making of pavement in between Basketball court & Lawn Tennis Court at IIIT Guwahati Campus. | 3,42,339.00 | 3,42,339.00 | Abdul Quddus | IIITG/Works/45/2024-25/278/270 | 27.11.2025 | 17.12.2025 | 15.12.2025 | 3,38,850.00
| 2025-26 | IIITG/Works/2025-26/ | Development of out side space adjucent to the Boys hostel kitchen and utensil cleaning aera at IIIT Guwahati Campus. | 89960 | 79920 | Anil Thakuria | IIITG/Works/Misc/2025-26/309 | 18.02.2026 | 16.02.2026 | 16.02.2026 | 79767
| 2025-26 | IIITG/WORKS/Misc/2024-25/294 | Land development Work of existing Children Park near Faculty Tower and in front of SAC building at IIIT Guwahati . | 188018 | 1,88,018 | M/S Adision Projects | IIITG/WORKS/Misc/2024-25/303 | 19.12.2025 | 10.01.2026 | 08.01.2026 | 187364
| 2025-26 | IIITG/WORKS/2023-24/300(A) | Water proofing work for seepage in the Room No 735 & 737 of Boys hostel IIIT Guwahati. | 71687.4 | 69810 | Deepak Das | IIITG/Works/Misc/2024-25/305 | 09.01.2026 | 05.02.2026 | 01.02.2026 | 69568
9 | 2024-25 | IIITG/Works/Misc/26.3/2024/249 | Construction of Car parking shed near Faculty Tower | Rs.26,15,127 | Rs.16,49,999 | M/S Adision Projects | IIITG/Works/Misc/26.3/2024/265 | 08.04.2025 | 07.05.2025 | 19.08.2025 | 19,29,321
10 | 2024-25 | IIITG/Works/14.1/259 | Compound Fencing at the North side of IIIT Guwahati Campus | Rs.17,11,044 | Rs.12,82,008 | Sri Pranab Thakuria | IIITG/Works/14.1/2025/264 | 07.04.2025 | 07.05.2026 | 13.08.2025 | 12,81,604
| 2024-25 | GEM/2025/B/6877320 | Security Services |  | 12888306 | Colnel Shishupal Security Consultancy & Services | GEM-511687723123152 | 01.03.2026 | 28.02.2027